MUSHROOMOS

PROCESS-2026C

470-HOUR STANDARD PROCESS

Final Process + Product Requirements Draft

| Status | DRAFT — for process-owner, GM, Production Manager and Laboratory sign-off |
| --- | --- |
| Standard | 470 hours from H0 to first grow-room loading |
| Worked example | Monday, 31 August 2026, 09:00 IST |
| Turner anchor | H174 — Monday, 07 September 2026, 15:00 |
| Purpose | Freeze the process and give the software one definition to build against |

SIGN-OFF Once approved, PROCESS-2026C v1 is frozen. Future changes create a new version and never rewrite an active batch baseline.

****Local Paddy is selected we will have only two soakings  so the time is decreased in this parallel process now I need my current sop to adapt for this change  so the normal flow of timings will be changed. Make an table and an example scenario for this case of local paddy .****

## 4.1 Paddy stream

| Activity | Example | Lab | Role |
| --- | --- | --- | --- |
| Bale weigh/cut/thread removal | H74→H86 · 12h | Moisture + dry weight | Parallel |
| Soaking 1 | H86→H108 · 22h | pH + EC + TDS | Parallel |
| Soaking 2 | H108→H136 · 28h | pH + EC + TDS | Parallel |
| Soaking 3 | H136→H160 · 24h | pH + EC + TDS | Must be ready at H160 |

# 1. Purpose and scope

This document is the single process baseline for the current MushroomOS build. It describes the physical factory process, parallel work, timing, laboratory controls, evidence requirements, Turner flow, bunker/tunnel flow, accountability and the decisions that must be confirmed before release.

Define the 470-hour standard from H0 to the first grow-room loading.

Make paddy, nitrogen/manure and laboratory work visible as parallel streams.

Define six Turner working piles and the M1/M2 execution model.

Define laboratory testing, evidence and hard approval gates.

Define plan vs actual vs variance vs extension without rewriting history.

Provide a single process reference for the software implementation.

## 1.1 The process mental model

# 2. Freeze rules

| Area | Current rule | Status |
| --- | --- | --- |
| Master clock | Continuous H0 → H470 | CONFIRMED |
| H0 | Admin selects the batch start time | CONFIRMED |
| Pre-H0 weighment | Advisory; never gates H0 | ADVISORY |
| Parallel streams | Paddy + nitrogen/manure + laboratory | CONFIRMED |
| Turner | ~6 piles; M1 + M2; T0→T1→T2→T3 | CONFIRMED |
| Turner laboratory | BEFORE T1 + AFTER T1 only; NO T0/T2/T3 test | CURRENT STAKEHOLDER RULE |
| Bunker grouping | P1+P2→B1; P3+P4→B2; P5+P6→B3 | CONFIRMED |
| Post-Turner bunker model | Two cycles, not the older three-cycle model | CONFIRMED |
| Bunker fills | 2h each; two hours apart | CONFIRMED |
| Tunnel process | 144h working standard within 135–155h range | FACTORY RANGE |
| Extensions | Separate authorization; baseline unchanged | CONFIRMED |
| Versioning | Future changes create a new process version | CONFIRMED |

SOURCE DISCIPLINE FACTORY CONFIRMED, FACTORY RANGE, PARALLEL, CONFIGURABLE, ADVISORY and UNRESOLVED remain distinct. Do not turn a simulation into a factory rule or invent unresolved values.

# 3. Exact worked timeline — H0 to H474

Example anchor: H0 = Monday, 31 August 2026, 09:00 IST. The timeline below follows the current PROCESS-2026C worked example.

| Time | H-hour | Process | Lab / control |
| --- | --- | --- | --- |
| 29 Aug ~23:00 | PRE-H0 | Raw material / bagasse weighment | Moisture, pH, ,EC,dry weight; advisory |
| 31 Aug 09:00 | H0 | Bagasse wetting + Hopper Pass 1 | Moisture, pH, EC, AFTER H1 |
| 31 Aug 12:00 | H3 | Material rest begins | — |
| 31 Aug 20:00 | H11 | Hopper Pass 2; dry or water branch | Moisture, pH, EC,AFTER H2 |
| 31 Aug 23:00 | H14 | Heap formation + rest | — |
| 01 Sep 11:00 | H26 | Before first bunker load / 2h bunker fill | LAB-04: moisture, pH, EC + evidence + GM gate |
| 01 Sep 13:00 | H28 | Conditioning begins | 45–55°C; first trigger ≥58°C or ≥60h |
| 03 Sep 11:00 | H74 | Paddy preparation starts | Moisture + dry weight |
| 03 Sep 23:00 | H86 | Paddy soak 1 | pH, EC, TDS |
| 04 Sep 01:00 | H88 | Bunker unload / reload | Moisture, pH, EC |
| 04 Sep 21:00 | H108 | Paddy soak 2 | pH, EC, TDS |
| 05 Sep 19:00 | H130 | Chicken manure + minerals weighment | Nitrogen, Ash |
| 05 Sep 21:00 | H132 | Rotavator dry mix | No water |
| 05 Sep 22:00 | H133 | Moisture decision | ≥68% proceed; <67% correct/retest; 67–68% unresolved |
| 06 Sep 01:00 | H136 | First convergence; CM mix begins | LAB-13 gate; nitrogen + ash |
| 06 Sep 09:00 | H144 to H146H1 , H147 to H149H2 | Water hopper pass+Another hopper pass | Target ~73% moisture; <45–50°C |
| 06 Sep 13:00 | H150 | Rest | 10h |
| 07 Sep 01:00 | H160 | Second convergence | Paddy ready; two equal piles |
| 07 Sep 05:00 | H164 | Add conditioned bagasse + CM mix | — |
| 07 Sep 07:00 | H166 | Flip 1 + Flip 2 | Back-to-back |
| 07 Sep 15:00 | H174 | TURNER START | Six working piles; M1 + M2 |
| 07 Sep 15:00–21:00 | H174–H180 | T0 | NO LAB AFTER T0 |
| 07 Sep ~18:00 onward | H177+ | T1 interleaved with T0 | LAB BEFORE / AFTER T1 only |
| 08 Sep 00:00 | H183 | T1 window complete | Post-T1 moisture per pile |
| 08 Sep onward | H186.5+ | T2 after each pile's 8h rest | NO LAB AFTER T2 |
| 08 Sep onward | H192.5+ | T3 | NO LAB AFTER T3 |
| 08 Sep 11:00 | H194 | Bunker 1 fill | P1+P2 |
| 08 Sep 13:00 | H196 | Bunker 2 fill | P3+P4 |
| 08 Sep 15:00 | H198 | Bunker 3 fill | P5+P6 |
| 11 Sep 04:00 | H259 | Bunker 1 reload | Height / moisture / full set |
| 11 Sep 06:00 | H261 | Bunker 2 reload | Same pattern |
| 11 Sep 08:00 | H263 | Bunker 3 reload | Same pattern |
| 13 Sep 21:00 | H324 | Tunnel loading stream 1 | Tunnel height + full lab gate |
| 13 Sep 23:00 | H326 | Tunnel loading stream 2 | — |
| 14 Sep 03:00 | H330 | Tunnel loading stream 3 | — |
| 14 Sep 05:00 | H332 | Tunnel filling complete | Tunnel process begins |
| 14–19 Sep | H332–H470 | Tunnel process | 144h working standard |
| 19 Sep 23:00 | H470 | First grow-room stream | Final QC |
| 20 Sep 01:00 | H472 | Second stream discharge | Final QC as configured |
| 20 Sep 03:00 | H474 | Final stream discharge | Full batch discharge |

# **the supervisor should track or input the bunker number and the tunnel number at their respective processes***

# 4. Parallel processes

Paddy is a parallel stream: it starts around H74, takes the current 86h operational sub-step total, and must be ready for the H160 convergence.

Nitrogen/manure preparation is a parallel stream: it opens around H130, is ready at H136, and its second laboratory result is a gate for mixing.

Laboratory work is operationally parallel across batches, but a result/approval can be a hard predecessor for downstream physical activity.

Parallel does not mean optional or irrelevant; a late parallel stream can delay a convergence.

## 4.1 Paddy stream

| Activity | Example | Lab | Role |
| --- | --- | --- | --- |
| Bale weigh/cut/thread removal | H74→H86 · 12h | Moisture + dry weight | Parallel |
| Soaking 1 | H86→H108 · 22h | pH + EC + TDS | Parallel |
| Soaking 2 | H108→H136 · 28h | pH + EC + TDS | Parallel |
| Soaking 3 | H136→H160 · 24h | pH + EC + TDS | Must be ready at H160 |

PADDY TOTAL The SOP states 74h in its headline, while the four actual sub-steps total 86h. PROCESS-2026C uses 86h because those are the operations actually performed. This stream is parallel, not added to the main rail.

# 5. Turner process

At H174 the material is laid out as approximately six physical working piles: P1–P6.

Two Turner machines are available: M1 and M2.

Piles progress independently. A pile may change machine during execution.

The Turner workbook is a machine/pile execution simulation; it is not a hardcoded UI sequence.

The system records actual pile, machine, operator, start/end and evidence.

## 5.1 Turner stages

| Stage | Physical operation | Timing | Lab |
| --- | --- | --- | --- |
| T0 | Dry Turner pass | ~7–8h / pile execution | NO LAB TEST |
| T1 | Water Turner pass | Current Turner schedule | LAB BEFORE T1 + LAB AFTER T1 |
| T2 | Next Turner pass | 8h rest from that pile's T1 end | NO LAB TEST |
| T3 | Final Turner pass | Current Turner schedule | NO LAB TEST |

CURRENT TURNER LAB RULE BEFORE T1 → moisture test per pile. AFTER T1 → moisture test per pile. NO laboratory test after T0, T2 or T3.

# 6. Laboratory process

***General Manager will have some remarks about the lab readings , like looking at the lab readings he will change some parameters such as how much water and all these things. The remarks that were put in by the general manager must go to the admin and as well as the lab technician so that he/she can intimate the remarks to the supervisor.***

| Process area | Current tests | Evidence | Control |
| --- | --- | --- | --- |
| Raw material | Moisture, pH, dry weight | Photo | Advisory |
| Bagasse / Hopper 1 / Hopper 2 | Moisture, pH, EC | Photo | Checkpoint |
| Before first bunker loading | Moisture, pH, EC | Photo | HARD GATE |
| Paddy weighment | Moisture, dry weight | Photo | Parallel |
| Paddy soak water 1/2/3 | pH, EC, TDS | Photo | Parallel |
| Chicken manure arrival | Nitrogen, Ash | Photo | Parallel |
| Chicken manure before mixing | Nitrogen, Ash | Photo | HARD GATE |
| Moisture decision | Moisture + branch | Photo | DECISION |
| Pre-Turner | Moisture, pH | Photo | Checkpoint |
| Before T1 | Moisture × P1–P6 | Photo as configured | Turner lab |
| After T1 | Moisture × P1–P6 | Photo as configured | Turner lab |
| After T0 | NO LAB TEST | — | Not in current process |
| After T2 | NO LAB TEST | — | Not in current process |
| After T3 | NO LAB TEST | — | Not in current process |
| Bunker loading | Height, pH, EC, moisture, N, Ash, C:N + observations | Photo | HARD GATE |
| Bunker reload | Shrunken height, moisture + pH/EC/moisture/N/Ash/C:N | Photo | Conditional |
| Before tunnel loading | Tunnel height | Photo | Checkpoint |
| Tunnel loading | pH, EC, moisture, N, Ash, C:N + observations | Photo | HARD GATE |
| Tunnel unload / final QC | pH, EC, moisture, N, Ash, C:N, shrunken height, actinomycetes + observations | Photo | Final QC |

LAB + PRODUCTION A technician can work on another batch while an approval is pending. Where the standard defines the lab result/approval as a predecessor, the Supervisor/Operator cannot start the downstream activity until the gate passes.

# 7. Evidence and photo requirements

Evidence is intended to let management later see what happened, not just a count of uploads.

| Activity class | Photos | Meaning | Final status |
| --- | --- | --- | --- |
| Normal operator-executed task | 2 where configured | 1 BEFORE/START + 1 AFTER/FINISH | Working standard |
| Laboratory checkpoint | Photo evidence required; exact count not consistently defined | Evidence of sample/test | PROCESS OWNER TO CONFIRM COUNT |
| Bunker / tunnel handling | Photo evidence where configured | Physical condition / handoff | PROCESS OWNER TO CONFIRM COUNT |
| Evidence correction | Original retained; replacement is additional history | Preserve provenance | Confirmed principle |

DO NOT INVENT PHOTO COUNTS The normal operator pattern is two photos. The source material does not provide a reliable per-checkpoint photo count for every laboratory/handling activity, so those counts are explicitly left as approval questions rather than guessed.

# 8. Baseline, actual, variance, extension

PLAN = SOP-generated baseline after Admin selects H0.

ACTUAL = what happened, recorded by execution actions.

VARIANCE = difference from the baseline, with cause where known.

EXTENSION = authorized additional time; it does not modify the baseline.

FORECAST = current expected result after actual progress and authorized exceptions.

| Layer | Example | Changes baseline? | Management sees |
| --- | --- | --- | --- |
| Plan | 15:00→22:00 | NO | What should happen |
| Actual | 17:00→00:00 | NO | What happened |
| Variance | +2h | NO | Why / how much |
| Extension | +2h approved | NO | Who authorized |
| Forecast | H472 | NO | Where it now lands |

# 9. Roles

| Role | Does | Does not |
| --- | --- | --- |
| Admin | Select H0; create/activate batch; permitted configuration | Rewrite active baseline |
| Operator | Open eligible task; Start; photos; Finish; photos | Enter/edit official timestamps |
| Laboratory | Test; readings; evidence; submit | Approve own result / bypass gate |
| Supervisor | Execute downstream activity when eligible | Start locked activity |
| Manager / GM | Review approvals and extensions | Rewrite history |
| System | Generate plan; enforce gates; record actuals | Invent factory rules |

# 10. Security and process integrity

ACCOUNTABILITY RULE The system must protect the facts that affect accountability: plan, actual timestamps, lab result, evidence, approval, deviation, extension, movement and machine usage.

Published process versions cannot be silently edited.

Activated baselines cannot be rewritten.

Normal operator execution does not accept an editable timestamp.

Lab gates are enforced server-side.

Submitted evidence and lab results remain traceable.

Extensions are separate from the plan.

Movement and machine-use history remain traceable.

The database is the enforcement point; UI hiding is not security.

# 11. What software must capture

Batch identity + process version.

H0 + generated planned timestamps.

Activity status and dependency state.

Actual start/end + actor + capture mode where offline.

Start/before and finish/after evidence where required.

Lab checkpoint + parameter + value + unit + actor + approval.

Pile + Turner stage + actual machine.

Physical movement source/destination.

Variance/deviation cause.

Extension request + approval + authorization.

Final QC + evidence.

ONE UI RULE Screens render backend answers. They do not calculate process sequence, gates, duration, variance, forecast, evidence requirements or official timestamps.

# 12. Approval and freeze

Signing below confirms that the process owner and responsible managers agree that PROCESS-2026C v1 is the process baseline for MushroomOS. Items explicitly listed as unresolved remain unresolved and are not to be invented in software.

| Role | Name | Signature / Date |
| --- | --- | --- |
| Process Owner |  |  |
| General Manager |  |  |
| Production Manager |  |  |
| Laboratory |  |  |

# 13. Source basis

Compost SOP.xlsx— current SOP.

TURNERPRCOESS.xlsx — Turner execution schedule / M1 / M2 / six-pile simulation.

lab_technician_batch_process.md — laboratory workflow, updated with the current stakeholder Turner-testing rule.

PROCESS-2026C / 470-Hour Standard Process — consolidated process draft.

Stakeholder clarifications recorded during process-owner review.

***Tunnel cleaning this is also a parallel activity stream where no tunnels can be filled if they aren’t cleaned this is an input entered by the  admin.

Bunker Cleaningthis is a parallel activity which needs to happen , this is will be monitered or the photos will be uploaded by the supervisor These options can be selected at the start they are optional and also they can be selected or changed in middle of the process and the photos needs to be uploaded by the supervisor ***

***Machinery Cleaning just photos , uploaded by the supervisor  admin will select the machinery which will be used at which process at the beginning all these things ***

WHAT I WANT :

1.For my understanding make UML diagrams Make architecture diagrams and make some Html screens for admin ,Lab and Supervisor . Anything to make this whole process more visual and easy to understand for building things.

2.Also look for a way where we need to have an option of editing the sop in a way that doesn’t effect exisiting tables and makes it easier when the sop is changed

3.Find ways where we track things easily like at turner 1 , 2 and 3 is where I am thinking the supervisors will try to find a workaround and skip work or cheat the entire system . Find the ways where the entire system can be cheated and loopholes that can be exploited.