## Read me
Baseline process table v3 — implementation specification FOR REVIEW. Nothing is in the database; no migration written.
Sources: Compost SOP.xlsx (31-08-2026) = main compost stages. TURNERPRCOESS.xlsx = explicit Turner / pile / bunker / tunnel values and sequence.
Execution is dependency/eligibility driven. Planned hours are informational; unresolved values are blank and flagged.
Yellow = conflict / unresolved / engine item. Blue rows = passive holds.
Counts: 40 generated production templates → 76 instances (Stage 0D row is documentation only, not generated). Lab: 23 templates → 47 instances (41 existing LAB-2026A + 6 Reload-2).
Sheets: 1 Production tasks · 2 Lab checkpoints · 3 Source conflicts · 4 Unresolved · 5 Engine changes · Confirmed.

## 1 Production tasks
# | Activity | Stage | Stream | Instance | Kind | Instruction (SOP wording) | Checklist ('+' actions only) | Duration | Minimum duration (h) | Maximum duration (h) | Dependency | Dependency type | Minimum rest | Evidence | Reading | Lab checkpoint / gate | Source | Conflict | Unresolved / engine | Turner clock (informational)
1 | New bagasse weighment | STAGE–0A: BAGASSE (NEW) PRE-WET & REST | Main bagasse | Batch | PERFORMED WORK | New bagasse : weighment | — | Not stated ('pre-ho-10') |  |  | None — available from activation | — | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C4:D4 · F4 'Optional' |  | U-01
2 | Wetting — 1st hopper pass | STAGE–0A: BAGASSE (NEW) PRE-WET & REST | Main bagasse | Batch | PHYSICAL OPERATION | Action : Wetting (1st hopper pass with full water+ target moisture 69-71%) | — | 3 h | 3 | 3 | None — available from activation | — | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Moisture % (target 69–71) | LAB-WET-01 · LAB-RM-01 (RECORD) | SOP C5:D5
3 | Rest | STAGE–0A: BAGASSE (NEW) PRE-WET & REST | Main bagasse | Batch | PASSIVE HOLD | Rest | — | 8 h | 8 | 8 | #2 finished | ALL | — | None (passive hold; nothing specified) | — (confirmation only) | — | SOP C6:D6 |  | E-2
4 | 2nd hopper pass | STAGE–0A: BAGASSE (NEW) PRE-WET & REST | Main bagasse | Batch | PHYSICAL OPERATION | Action : 2nd Hopper pass (dry/with sufficent water to reach target mosture) | — | 3 h | 3 | 3 | #3 confirmed | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Moisture % ('reach target moisture') | LAB-WET-02 (RECORD) | SOP C7:D7
5 | Heap formation + resting | STAGE–0A: BAGASSE (NEW) PRE-WET & REST | Main bagasse | Batch | PHYSICAL OPERATION | Action :Heap formation (height ≤1.5mts) + resting | Heap formation (height ≤1.5mts) ¦ resting | 12 h | 12 | 12 | #4 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Heap height m (target ≤1.5) | — | SOP C8:D8 |  | U-17
6 | Flipping + bunker filling | STAGE–0B: 1st BUNKER FILLING & CONDITIONING | Main bagasse | Batch | PHYSICAL OPERATION | Action : Flipping + bunker filling (ht 2.6-2.7mts) without water | Flipping ¦ bunker filling (ht 2.6-2.7mts) without water | 2 h | 2 | 2 | #5 finished + LAB-BNK-PRE approved by GM | ALL + LAB GATE | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Fill height m (target 2.6–2.7) | LAB-BNK-PRE (GATE → GM) | SOP C10:D10
7 | Resting period — unloading trigger | STAGE–0B: 1st BUNKER FILLING & CONDITIONING | Main bagasse | Batch | PASSIVE HOLD + TRIGGER CONFIRMATION | Resting period & temp 45-55°C · Unloading trigger ≥ 58 °C &Time ≥ 60 hrs | — | 60 h | 60 | 60 | #6 finished | ALL | — | None as photo; the trigger confirmation reading is the record | Temperature °C at confirmation (trigger ≥58 °C AND ≥60 h) | — | SOP C11:D12 |  | E-2
8 | Unloading, flipping, reloading to new bunker | STAGE–0C: UNLOADING AND RE-LOADING | Main bagasse | Batch | PHYSICAL OPERATION | Action : Loader unloading, Flipping and Reloading to new bunker (without water) · Temp: 45–58 °C + Fill height: 2.2–2.4 ; Rest : 40 hrs | — (no '+' between actions; '+' in C15 is a target) | 5 h | 5 | 5 | #7 confirmed | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Temperature °C (target 45–58) · Fill height m (target 2.2–2.4) | LAB-UNL-01 · LAB-HOP-PRE · LAB-RLD-01 (RECORD) | SOP C14:D15 | C-01
9 | Rest — start unloading at trigger | STAGE–0C: UNLOADING AND RE-LOADING | Main bagasse | Batch | PASSIVE HOLD + TRIGGER CONFIRMATION | Action : Whenever Temp reaches 58 °C OR crossing 40 Hrs Start Unloading | — | 40 h | 40 | 40 | #8 finished | ALL | — | None as photo; the trigger confirmation reading is the record | Temperature °C at confirmation (trigger ≥58 °C OR ≥40 h) | — | SOP C16:D16 | C-01 | E-2
10 | Unload with moisture decision | STAGE–0C: UNLOADING AND RE-LOADING | Main bagasse | Batch | PHYSICAL OPERATION | UNLOAD TRIGGER Temp ≥ 58 °C OR Time ≥ 40 hrs; If Moisture ≥ 68 % → Proceed /If Moisture < 67 % → Controlled mist with hopper | — | 3 h | 3 | 3 | #9 confirmed | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Moisture % (≥68 proceed / <67 controlled mist) | LAB-MOIST-DEC (DECISION — does not lock) | SOP C17:D17 | C-01 | U-02
11 | Stage 0D — UNRESOLVED (documentation only; no task generated) | STAGE–0D 2nd BUNKER RE-FILLING & CONDITIONING | Main bagasse | — | UNRESOLVED STAGE | UNLOAD TRIGGER Temp ≥ 58 °C OR Time ≥ 40 hrs · 2nd bunker reloading depends on the 1st reloading temperature and holding time | — | 24 h (stage heading only) |  |  | Not generated. The dependency it implies is NOT deleted: #14's main-stream dependency is UNRESOLVED and blocks #14 | UNRESOLVED | — | — | — | — | SOP C18:D20 |  | U-03
12 | CM + gypsum + AS weighment | STAGE–1A: CHICKEN MANURE + MINERALS (DRY) MIX | Nitrogen/mineral | Batch | PERFORMED WORK | Materials: CM + Gypsum + AS WEIGHMENT | — ('+' joins materials; not split) | 2 h | 2 | 2 | None — available from activation (parallel) | — | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-CM-ARR (RECORD) | SOP C22:D22
13 | Dry mix + rotavator | STAGE–1A: CHICKEN MANURE + MINERALS (DRY) MIX | Nitrogen/mineral | Batch | PHYSICAL OPERATION | Action: Dry mix+ use Rotovator for breaking manure lumps | Dry mix ¦ use Rotovator for breaking manure lumps | 4 h | 4 | 4 | #12 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C23:D23
14 | Add CM mix + loader mixing + flipping 1 + flipping 2 | STAGE–1B: CONDITIONED BAGASSE + MIXING OF DRY NITROGEN | Convergence/yard | Batch | PHYSICAL OPERATION | Action : Add Chicken Manure(CM) Mix on conditioned bagasse + Loader mixing + Flipping 1+ Flipping 2 BACK TO BACK | Add Chicken Manure(CM) Mix on conditioned bagasse ¦ Loader mixing ¦ Flipping 1 ¦ Flipping 2 BACK TO BACK | 8 h | 8 | 8 | #13 finished + LAB-CM-USE approved by GM + MAIN-STREAM DEPENDENCY UNRESOLVED (U-03) — execution blocked until the rule is defined | ALL + LAB GATE + UNRESOLVED (blocked · E-5) | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-CM-USE (GATE → GM) | SOP C25:D25 |  | U-03 · E-5
15 | Hopper pass + another hopper pass + rest 10 h | STAGE–1B: CONDITIONED BAGASSE + MIXING OF DRY NITROGEN | Convergence/yard | Batch | PHYSICAL OPERATION | Action : Hopper pass with full (Target: 73% moisture+Temperature < 45–50 °C). Another Hopper Pass , plus rest of 10 hours | — ('+' is inside a target/value; not split) | 16 h | 16 | 16 | #14 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Moisture % (target 73) · Temperature °C (target <45–50) | — | SOP C26:D26 |  | U-15
16 | Paddy bales weighment + cutting + threads removal | STAGE–1C-A: PADDY PREPARATION | Paddy (parallel) | Batch | PERFORMED WORK | Action :paddy bales weighment+ cutting+threads removal | paddy bales weighment ¦ cutting ¦ threads removal | 12 h | 12 | 12 | None — available from activation (parallel) | — | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-PDY-WGH (RECORD) | SOP C29:D29 · E28 'parallel process … converted to the bagasse mix timing' | C-02
17 | Soaking 1 | STAGE–1C-A: PADDY PREPARATION | Paddy (parallel) | Batch | PHYSICAL OPERATION | Soaking 1 :- Pushing in + Tilting 1 + Tilting 2 + Pushing out(8-10 hours) + Resting in bunkers(10-12hrs) | Pushing in ¦ Tilting 1 ¦ Tilting 2 ¦ Pushing out(8-10 hours) ¦ Resting in bunkers(10-12hrs) | 22 h | 22 | 22 | #16 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-PDY-S1 (RECORD) | SOP C30:D30 · E28 'parallel process … converted to the bagasse mix timing' | C-02 | U-17
18 | Soaking 2 | STAGE–1C-A: PADDY PREPARATION | Paddy (parallel) | Batch | PHYSICAL OPERATION | Soaking 2 :- Pushing in + Tilting 1 + Tilting 2 + Pushing out(8-10 hours) + Resting in bunkers(18hrs) | Pushing in ¦ Tilting 1 ¦ Tilting 2 ¦ Pushing out(8-10 hours) ¦ Resting in bunkers(18hrs) | 28 h | 28 | 28 | #17 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-PDY-S2 (RECORD) | SOP C31:D31 · E28 'parallel process … converted to the bagasse mix timing' | C-02 | U-17
19 | Soaking 3 | STAGE–1C-A: PADDY PREPARATION | Paddy (parallel) | Batch | PHYSICAL OPERATION | Soaking 3 :- Pushing in + Tilting 1+ Tilting 2 + Pushing out(8-10 hours) + Resting in bunkers(12-14hrs) | Pushing in ¦ Tilting 1 ¦ Tilting 2 ¦ Pushing out(8-10 hours) ¦ Resting in bunkers(12-14hrs) | 24 h | 24 | 24 | #18 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-PDY-S3 (RECORD) | SOP C32:D32 · E28 'parallel process … converted to the bagasse mix timing' | C-02 | U-17
20 | Preparation of 2 equal piles on platform | STAGE–1C-A: PADDY PREPARATION | Paddy (parallel) | Batch | PHYSICAL OPERATION | Preparation of 2 equal piles on platform(4hrs) | — | 4 h | 4 | 4 | #19 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C33:D33 · E28 'parallel process … converted to the bagasse mix timing' | C-02
21 | Add bagasse + CM mix onto 2 paddy piles | STAGE–1C-B: PADDY + BAGASSE + MINERAL MIXING | Convergence/yard | Batch | PHYSICAL OPERATION | Action : Add Bagasse+ CM mix gradually on 2 paddy piles | — ('+' joins materials; not split) | 2 h | 2 | 2 | #15 finished + #20 finished | ALL (convergence) | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C35:D35
22 | Flipping 1 + flipping 2 back to back | STAGE–1C-B: PADDY + BAGASSE + MINERAL MIXING | Convergence/yard | Batch | PHYSICAL OPERATION | Action :Flipping 1+ Flipping 2 BACK TO BACK | Flipping 1 ¦ Flipping 2 BACK TO BACK | 8 h | 8 | 8 | #21 finished | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-PRE-T (RECORD) | SOP C36:D36
23 | Turner T0 | PHASE–1A: T0 & T1 CONTINUOUS NO GAP | Convergence/yard | Pile 1–6 (one instance per pile) | TURNER OPERATION | Action: Dry Turner pass (TO) without water (Estimated piles : 6 ), (No.of. Turner's : 2 ) | — | 1.5 h per pile (Turner) | 1.5 | 1.5 | #22 finished | ALL (each pile) | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C38:D38 · TURNER A2:S13 | C-03 |  | P1 09:00–10:30 · P2 10:30–12:00 · P3 09:00–10:30 · P4 10:30–12:00 · P5 12:00–13:30 · P6 13:30–15:00 (Day 1)
24 | Turner T1 | PHASE–1A: T0 & T1 CONTINUOUS NO GAP | Convergence/yard | Pile 1–6 (one instance per pile) | TURNER OPERATION | PHASE-1: T1 (immediately after TO ) with water (No.of. Turner's : 2 ) | — | 1.5 h per pile (Turner) | 1.5 | 1.5 | T0 of the same pile finished | ALL · same pile | — (Turner gap 1.5/3/3/4.5/1.5/1.5 h: informational) | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-T1-PRE-Pn · LAB-T1-POST-Pn (RECORD) | SOP C39 · TURNER A15:S27 | C-03 · C-04 |  | P1 12:00–13:30 · P2 15:00–16:30 · P3 13:30–15:00 · P4 16:30–18:00 · P5 15:00–16:30 · P6 16:30–18:00 (Day 1)
25 | Turner T2 | PHASE–1B: T2 & T3 | Convergence/yard | Pile 1–6 (one instance per pile) | TURNER OPERATION | PHASE–1B: T2 & T3 · Action: 8 Hrs rest between T1&T2 | — | 1.5 h per pile (Turner) | 1.5 | 1.5 | T1 of the same pile finished | ALL · same pile | 8 h after that pile's T1 actual finish (SOP C40 = Turner) | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C40:D41 · TURNER A28:S40 | C-03 |  | P1 21:30–23:00 D1 · P2 00:30–02:00 D2 · P3 23:00 D1–00:30 D2 · P4 02:00–03:30 D2 · P5 00:30–02:00 D2 · P6 02:00–03:30 D2
26 | Turner T3 | PHASE–1B: T2 & T3 | Convergence/yard | Pile 1–6 (one instance per pile) | TURNER OPERATION | Action: T3 immediately after T2 | — | 1.5 h per pile (Turner) | 1.5 | 1.5 | T2 of the same pile finished | ALL · same pile | — (Turner gap 4.5/3/3/1.5/4.5/3 h: informational) | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C42 · TURNER A41:S53 | C-03 · C-04 |  | P1 03:30–05:00 · P2 05:00–06:30 · P3 03:30–05:00 · P4 05:00–06:30 · P5 06:30–08:00 · P6 06:30–08:00 (Day 2)
27 | Bunker filling | PHASE–1C BUNKER FILLING 1 | Bunker line | B1 (P1+P2) · B2 (P3+P4) · B3 (P5+P6) | PHYSICAL OPERATION | Action :Bunker filling starts immediately after 3-4 piles completion (Ht 2.6-2.7 m) without water | — | 2 h per bunker (Turner) | 2 | 2 | T3 of the first pile of the pair finished (P1 / P3 / P5) + LAB-BNK-LOAD-Bn approved by GM | ALL + LAB GATE | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Fill height m (target 2.6–2.7) | LAB-BNK-LOAD-Bn (GATE → GM) | SOP C44:D44 · TURNER A54:S66 | C-05 · C-14 |  | B1 05:00–07:00 · B2 07:00–09:00 · B3 09:00–11:00 (Day 2)
28 | Holding 1 — reload trigger | PHASE–1C BUNKER FILLING 1 | Bunker line | B1 · B2 · B3 (one instance per bunker) | PASSIVE HOLD + TRIGGER CONFIRMATION | Holding Duration :48 hours After attaining 70°C +15 HRS TO REACH 70 · Action: Reload trigger Temp 73–74 °C + Duration 48+ hours, start unload and load in to another bunker | — ('+' is inside a target/value; not split) | 63 h (15 h to reach 70 °C + 48 h) | 63 | 63 | #27 same bunker finished | ALL · same bunker | — | None as photo; the trigger confirmation reading is the record | Temperature °C at confirmation (reload trigger 73–74 °C + 48+ h) | — | SOP C45:D46 · TURNER row 67 | C-06 | E-2 · U-08
29 | Unload & reload 1 | PHASE–1D-A UNLOAD & RELOAD – 1 | Bunker line | B1 · B2 · B3 (one instance per bunker) | PHYSICAL OPERATION | Bunker filling (SOP) · 'Bunker Reloading' (Turner) | — | 2 h per bunker (Turner) | 2 | 2 | #28 same bunker confirmed | ALL · same bunker | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-RLD-UNL-Bn · LAB-RLD-RE-Bn (RECORD) | SOP C48:D48 · TURNER A68:S79 | C-07 |  | B1 22:00–24:00 D4 · B2 00:00–02:00 D5 · B3 02:00–04:00 D5
30 | Holding 2 — unload trigger | PHASE–1D-A UNLOAD & RELOAD – 1 | Bunker line | B1 · B2 · B3 (one instance per bunker) | PASSIVE HOLD + TRIGGER CONFIRMATION | Holding Duration : 45 hours After attaining 68°C · Action: unload trigger Temp 70 °C+Duration 36+ hrs,start unload and RELOAD | — ('+' is inside a target/value; not split) | 60 h (15 h to reach 68 °C + 45 h) | 60 | 60 | #29 same bunker finished | ALL · same bunker | — | None as photo; the trigger confirmation reading is the record | Temperature °C at confirmation (unload trigger 70 °C + 36+ h) | — | SOP C49:D50 · TURNER row 80 | C-08 · C-09 | E-2 · U-08
31 | Reload 2 — OPTIONAL (skip with reason) | PHASE–1D-B UNLOAD & RELOAD – 2 | Bunker line | B1 · B2 · B3 (one instance per bunker) | PHYSICAL OPERATION | Bunker filling (Reload 2) | — | 10 h | 10 | 10 | #30 same bunker confirmed | ALL · same bunker | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-RLD2-UNL-Bn · LAB-RLD2-RE-Bn (RECORD) | SOP C52:D52 | C-10
32 | Holding 3 — unload into tunnel | PHASE–1D-B UNLOAD & RELOAD – 2 | Bunker line | B1 · B2 · B3 (one instance per bunker) | PASSIVE HOLD + TRIGGER CONFIRMATION | Holding Duration : 24 hours After attaining 68°C · Action: unload trigger Temp 70 °C+Duration 24 hrs,start unload and load into a tunnel | — ('+' is inside a target/value; not split) | 30–36 h | 30 | 36 | #31 same bunker — rule after a skipped Reload 2 UNRESOLVED (U-04); blocked until decided | UNRESOLVED (blocked · E-5; E-3 only once U-04 is decided) | — | None as photo; the trigger confirmation reading is the record | Temperature °C at confirmation (unload trigger 70 °C + 24 h) | — | SOP C53:D54 | C-11 | U-04 · E-5 · E-2
33 | Tunnel preparation | PHASE–2A TUNNEL PREPERATION | Tunnel | Tunnel (one) | PERFORMED WORK | Action: After tunnel wash + gliding net should be tight fix to the total grid area + Clean and dry probes & hang probably · Action: Remove and wash nets (wash with high pressure water No folds & dirt + stich damages) · Action:Leave 6.0mts of Pulling net at wynch side( for unloading) | After tunnel wash ¦ gliding net should be tight fix to the total grid area ¦ Clean and dry probes & hang probably (C56 only; '+' in C57 is inside a condition) | 8 h | 8 | 8 | Not stated by either source — blocked until defined | UNRESOLVED (blocked · E-5) | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-TUN-PRE (RECORD) | SOP C55:D58 |  | U-05 · U-16 · U-17 · E-5
34 | Tunnel filling | PHASE–2B TUNNEL FILLING | Tunnel | B1 → B2 → B3 (serial, one tunnel) | PHYSICAL OPERATION | Action:After 36hrs of Reloading 2, start load in to Tunnel | — | 2 h per bunker (Turner) | 2 | 2 | #32 same bunker + #33 + previous bunker's tunnel filling (Turner order) + LAB-TUN-LOAD-Bn approved by GM (stays locked while #32 and #33 are blocked) | ALL + LAB GATE | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | LAB-TUN-LOAD-Bn (GATE → GM) | SOP C60:D60 · TURNER A81:S92 | C-12 · C-14 | U-04 · U-05 (via #32, #33) | B1 15:00–17:00 · B2 17:00–19:00 · B3 21:00–23:00 (Day 7)
35 | Levelling & conditioning | PHASE–2C TUNNEL PROCESS | Tunnel | Tunnel (one) | PHYSICAL OPERATION | Action: Levelling&conditioning | — | 14 h | 14 | 14 | Tunnel filling — which instance(s) not stated (U-06); blocked until defined | UNRESOLVED (blocked · E-5) | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | — | — | SOP C62:D62 · TURNER row 93 '144 Hrs (6 Days)' |  | U-06 · E-5
36 | Heating up | PHASE–2C TUNNEL PROCESS | Tunnel | Tunnel (one) | PASSIVE HOLD | Heating up | — | 12 h | 12 | 12 | #35 finished | ALL | — | None (passive hold; nothing specified) | — (confirmation only) | — | SOP C63:D63 · TURNER row 93 '144 Hrs (6 Days)' |  | E-2
37 | Pasteurization | PHASE–2C TUNNEL PROCESS | Tunnel | Tunnel (one) | PASSIVE HOLD | Pasteurization | — | 8 h | 8 | 8 | #36 confirmed | ALL | — | None (passive hold; nothing specified) | — (confirmation only) | — | SOP C64:D64 · TURNER row 93 '144 Hrs (6 Days)' |  | E-2
38 | Cooling down 1 | PHASE–2C TUNNEL PROCESS | Tunnel | Tunnel (one) | PASSIVE HOLD | Cooling down 1 | — | 12–14 h | 12 | 14 | #37 confirmed | ALL | — | None (passive hold; nothing specified) | — (confirmation only) | — | SOP C65:D65 · TURNER row 93 '144 Hrs (6 Days)' |  | E-2
39 | Conditioning 2 | PHASE–2C TUNNEL PROCESS | Tunnel | Tunnel (one) | PASSIVE HOLD | Conditioning 2 | — | 80–85 h | 80 | 85 | #38 confirmed | ALL | — | None (passive hold; nothing specified) | — (confirmation only) | — | SOP C66:D66 · TURNER row 93 '144 Hrs (6 Days)' |  | E-2
40 | Start cooling down 2 | PHASE–2C TUNNEL PROCESS | Tunnel | Tunnel (one) | UNRESOLVED (U-11) | Action: Start Cooling down 2 | — | 8–14 h | 8 | 14 | #39 confirmed | ALL | — | Depends on U-11 | — | — | SOP C67:D67 · TURNER row 93 '144 Hrs (6 Days)' |  | U-11
41 | Tunnel unloading / grow-room loading | PHASE–2D TUNNEL UNLOADING | Tunnel | Stream B1 · B2 · B3 (Turner GR loading) | PHYSICAL OPERATION | Action :At 24 degree start unloading compost | — | Not stated |  |  | #40 confirmed; B2 after B1, B3 after B2 (Turner order) | ALL | — | Before + after photo, taken after Start (confirmed operational evidence model: prompt.md §6–7 Supervisor flow) | Temperature °C (start at 24) | LAB-QC-FINAL (RECORD, stream 1) | SOP C68:C69 · TURNER A94:S94 | C-13 | U-07 | GR loading starts B1 17:00 · B2 19:00 · B3 21:00 (Day 13)

## 2 Lab checkpoints
Checkpoint | Kind | Instance | Binding (production task) | MIGRATED behaviour (existing) | LAB-2026A timing (source) | Timing PROPOSAL — NOT migrated (U-12) | Proposal would need | Evidence (existing) | Parameters (existing) | Unresolved / conflict
LAB-RM-01 | RECORD | Batch | #2 (existing) | Available from activation (existing behaviour: no lab entry gate) | PRE-H0 · incoming lot, before the clock starts | Available from activation | — | Lot photo + weighment slip | moisture_pct, ph, dry_weight
LAB-WET-01 | RECORD | Batch | #2 (existing) | Available from activation (existing behaviour: no lab entry gate) | 0A · during / at the end of hopper pass 1 | #2 started — or #2 finished | Needs E-4 ('started' predecessor) / ALL | Sample photo | moisture_pct, ph, ec | U-12
LAB-WET-02 | RECORD | Batch | #4 (existing) | Available from activation (existing behaviour: no lab entry gate) | 0A · at the end of hopper pass 2 | #4 finished | ALL | Sample photo | moisture_pct, ph, ec | U-12
LAB-BNK-PRE | GATE | Batch | #6 (existing) | Available from activation (existing behaviour: no lab entry gate) · locks its bound production task until the GM approves (existing LAB_APPROVED) | 0A→0B · immediately before bunker filling begins | #5 finished; locks #6 until GM approves | ALL | Sample photo | moisture_pct, ph, ec | U-12
LAB-UNL-01 | RECORD | Batch | #8 (existing) | Available from activation (existing behaviour: no lab entry gate) | 0C · at unload, on the sample taken | #8 started | Needs E-4 ('started' predecessor) | Sample photo | moisture_pct, ph, ec | U-12
LAB-HOP-PRE | RECORD | Batch | #8 (existing) | Available from activation (existing behaviour: no lab entry gate) | 0C · between unload and the hopper pass | Not determinable in 0C (hopper appears in #10) | UNRESOLVED | Sample photo | moisture_pct, ph, ec | U-12
LAB-RLD-01 | RECORD | Batch | #8 (existing) | Available from activation (existing behaviour: no lab entry gate) | 0C · during reload | #8 started | Needs E-4 ('started' predecessor) | Sample photo | moisture_pct, ph, ec | U-12
LAB-MOIST-DEC | DECISION | Batch | #10 (existing) | Available from activation (existing behaviour: no lab entry gate) · informs its production task; does not lock | 0C→1B · after the second conditioning cycle | #9 confirmed; informs #10, does not lock | ALL | Sample photo | moisture_pct | U-12
LAB-CM-ARR | RECORD | Batch | #12 (existing) | Available from activation (existing behaviour: no lab entry gate) | 1A · when the manure is received | Available from activation | — | Lot photo | moisture_pct, ph, n_pct, ash_pct
LAB-CM-USE | GATE | Batch | #14 (existing) | Available from activation (existing behaviour: no lab entry gate) · locks its bound production task until the GM approves (existing LAB_APPROVED) | 1A→1B · on unload for the final mix | #13 finished; locks #14 until GM approves | ALL | Sample photo | moisture_pct, ph, n_pct, ash_pct | U-12
LAB-PDY-WGH | RECORD | Batch | #16 (existing) | Available from activation (existing behaviour: no lab entry gate) | 1C-A · at bale weighment, before soaking | #16 started | Needs E-4 ('started' predecessor) | Weighment slip | moisture_pct, dry_weight | U-12
LAB-PDY-S1 / S2 / S3 | RECORD | Batch | #17 / #18 / #19 (existing) | Available from activation (existing behaviour: no lab entry gate) | 1C-A · during soaking 1 / 2 / 3 | #17 / #18 / #19 started | Needs E-4 ('started' predecessor) | Sample photo | ph, ec, tds | U-12
LAB-PRE-T | RECORD | Batch | #22 (existing) | Available from activation (existing behaviour: no lab entry gate) | 1C-B · after the second yard flip, before the Turner begins | #22 finished | ALL | Sample photo | moisture_pct, ph | U-12
LAB-T1-PRE-P1…P6 | RECORD | Pile 1–6 | #24 same pile (existing) | Available from activation (existing behaviour: no lab entry gate) | Turner · after T0, before T1 — one reading per pile | T0 of the same pile finished | ALL · same pile | Sample photo | moisture_pct | U-12
LAB-T1-POST-P1…P6 | RECORD | Pile 1–6 | #24 same pile (existing) | Available from activation (existing behaviour: no lab entry gate) | Turner · immediately after T1 — one reading per pile | T1 of the same pile finished | ALL · same pile | Sample photo | moisture_pct | U-12
LAB-BNK-LOAD-B1…B3 | GATE | B1–B3 | #27 same bunker (existing) | Available from activation (existing behaviour: no lab entry gate) · locks its bound production task until the GM approves (existing LAB_APPROVED) | 1C · at each bunker fill — one per bunker | Same opening as #27 (first pile's T3); locks #27 until GM approves | ALL · same bunker | Before photo + height photo | bunker_height, ph, ec, moisture_pct, n_pct, ash_pct, cn_ratio, smell, colour, spring | U-12 · C-14
LAB-RLD-UNL-B1…B3 | RECORD | B1–B3 | #29 same bunker (existing) | Available from activation (existing behaviour: no lab entry gate) | 1D-A · at unload, before reloading | #28 same bunker confirmed | ALL · same bunker | Height photo | shrunken_height, moisture_pct | U-12
LAB-RLD-RE-B1…B3 | RECORD | B1–B3 | #29 same bunker (existing) | Available from activation (existing behaviour: no lab entry gate) | 1D-A · during reload | #29 started | Needs E-4 ('started' predecessor) | Sample photo | ph, ec, moisture_pct, n_pct, ash_pct, cn_ratio, smell, colour, spring | U-12
LAB-RLD2-UNL-B1…B3 | RECORD | B1–B3 | #31 same bunker — NEW binding (LAB-2026A 1D-B explicit) | Available from activation (existing behaviour: no lab entry gate) | 1D-B · at unload, before the second reload — only where the process runs a second reload | #31 started (must not open if Reload 2 is skipped) | Needs E-4 ('started' predecessor) | Height photo (checkpoint as defined) | shrunken_height, moisture_pct | U-12 · U-04
LAB-RLD2-RE-B1…B3 | RECORD | B1–B3 | #31 same bunker — NEW binding (LAB-2026A 1D-B explicit) | Available from activation (existing behaviour: no lab entry gate) | 1D-B · during the second reload | #31 started | Needs E-4 ('started' predecessor) | Sample photo (checkpoint as defined) | ph, ec, moisture_pct, n_pct, ash_pct, cn_ratio, smell, colour, spring | U-12
LAB-TUN-PRE | RECORD | Tunnel | #34 B1 (existing) | Available from activation (existing behaviour: no lab entry gate) | 2A · after tunnel preparation, before filling | #33 finished | ALL | Tunnel photo | tunnel_height | U-12
LAB-TUN-LOAD-B1…B3 | GATE | B1–B3 | #34 same bunker (existing) | Available from activation (existing behaviour: no lab entry gate) · locks its bound production task until the GM approves (existing LAB_APPROVED) | 2B · during tunnel filling | Locks #34 until GM approves, yet source says 'during' (C-14) | Needs E-4 ('started' predecessor) · C-14 | Before photo | ph, ec, moisture_pct, n_pct, ash_pct, cn_ratio, smell, colour, spring | U-12 · C-14
LAB-QC-FINAL | RECORD | Stream 1 | #41 stream B1 (existing) | Available from activation (existing behaviour: no lab entry gate) | 2D · at 24 °C, when unloading begins | #41 B1 started | Needs E-4 ('started' predecessor) | Sample photo + after photo | ph, ec, moisture_pct, n_pct, ash_pct, cn_ratio, shrunken_height, actinomycetes, smell, colour, spring | U-12

## 3 Source conflicts
ID | Between | Process area | Disagreement | Governs | Handling
C-01 | 31-08 SOP (internal) | Main compost | Stage 0C heading 8 h; its lines 5 + 40 + 3 = 48 h | SOP | Lines kept as tasks #8–#10; conflict carried
C-02 | 31-08 SOP (internal) | Main compost | Paddy 1C-A heading 74 h; lines 12 + 22 + 28 + 24 + 4 = 90 h | SOP | Lines kept as tasks #16–#20; conflict carried
C-03 | SOP vs TURNERPRCOESS | Turner | Phase 1A 'T0 15 h' (23 h), 1B 16 h vs Turner T0+T1 all piles 9 h, T2+T3 10.5 h | TURNER | Per-pile values from Turner
C-04 | SOP vs TURNERPRCOESS | Turner | SOP 'T1 immediately after T0 / no gap', 'T3 immediately after T2' vs Turner gaps 1.5–4.5 h | TURNER | Gaps informational, not enforced
C-05 | SOP vs TURNERPRCOESS | Bunker | Fill 'after 3–4 piles completion', 8 h vs Turner 2 h/bunker from first pile of pair | TURNER (locked decision) | First pile of pair
C-06 | 31-08 SOP (internal) | Bunker | 1C holding '48 h after attaining 70 °C' vs reload trigger '73–74 °C + 48+ h' | SOP | Both shown; Supervisor confirms
C-07 | SOP vs TURNERPRCOESS | Bunker | Reload 1: SOP 8 h vs Turner 2 h/bunker | TURNER | Turner value
C-08 | 31-08 SOP (internal) | Bunker | 1D-A holding '45 h after attaining 68 °C' vs unload trigger '70 °C + 36+ h' | SOP | Both shown; Supervisor confirms
C-09 | TURNERPRCOESS (internal) | Bunker/tunnel | Hold 2 labelled 15 + 45 = 60 h; tunnel loading scheduled 63 / 63 / 65 h after reload | TURNER | Both shown
C-10 | SOP vs TURNERPRCOESS | Bunker | Reload 2 (1D-B) in SOP; absent in Turner | Locked decision | Optional, skip with reason
C-11 | 31-08 SOP (internal) | Bunker/tunnel | 1D-B holding 30–36 h vs trigger '70 °C + 24 h' vs 2B 'after 36 hrs of Reloading 2' | SOP | Both shown; Supervisor confirms
C-12 | SOP vs TURNERPRCOESS | Tunnel | Tunnel filling '36 h after reloading 2' vs Turner 63 / 63 / 65 h after reload 1 | TURNER (sequence) | Eligibility by dependency; both shown
C-13 | TURNERPRCOESS (internal) | Tunnel | B3 grow-room loading 142 h after its tunnel load; B1/B2 144 h | TURNER | Informational
C-14 | LAB-2026A vs existing gate model | Lab | LAB-BNK-LOAD 'at each bunker fill' and LAB-TUN-LOAD 'during tunnel filling' are GATEs that lock those same activities until GM approval | Existing model kept | Flagged

## 4 Unresolved
ID | Area | Open question
U-01 | 0A weighment | Meaning of 'pre-ho-10'; whether 'Optional' means skip with reason
U-02 | 0C moisture | Rule for moisture between 67 % and 68 %
U-03 | Stage 0D | No task lines. No tasks generated; no predecessor chain through 0D; #14's main-stream dependency is unresolved
U-04 | Reload 2 skipped | Factory rule for what follows a skipped Reload 2. Until decided, Holding 3 (#32) is blocked (E-5) — a skip must not open it; E-3 is implemented only once this is decided
U-05 | Tunnel preparation | No start condition in either source
U-06 | Tunnel clock | Tunnel process after all three fillings (SOP phases) or per stream (Turner 144 h per stream)
U-07 | 2D unloading | No duration; SOP one unloading line vs Turner three grow-room loadings
U-08 | Hold hours vs trigger text | C-06, C-08, C-11 disagree — both displayed; no rule chosen
U-09 | Hold evidence | No photos specified on passive holds — none required unless you specify
U-11 | Cooling down 2 | 'Action: Start Cooling down 2' with 8–14 h — performed start or passive hold
U-12 | Lab timing | DEFERRED. Timing proposals are documentation only and are NOT migrated. Migrated behaviour = existing: every lab checkpoint available from activation; GATE checkpoints lock their production task until GM approval
U-13 | Planned hours | Absolute H-hours cannot be stated without resolving C-01, C-02, U-03. Planning stays unresolved; execution stays valid (E-1)
U-14 | Reading bands | Text target only, or numeric band — a numeric band turns an out-of-range reading into a DEVIATION that holds the next task in its stream (existing behaviour)
U-15 | 1B 16 h line | Kept as one task; per-pass durations not stated
U-16 | 2A structure | Three action lines, one 8 h value — kept as one task
U-17 | Borderline checklist splits | 'resting' (#5), 'Resting in bunkers (…)' (#17–#19), 'After tunnel wash' (#33) — confirm they are actions
U-18 | Authority over unresolved dependencies | Open. P-1 (GM approval) is NOT applied: a GM approval would not define 0D, the tunnel-preparation start or the tunnel clock. These stay blocked until the factory rule is defined
U-19 | Consequence of blocking (for review) | A batch run live stops at #14 (1B) until U-03 is defined — 0A–0C, 1A and paddy still run. Holding 3 (#32), tunnel preparation (#33) and therefore tunnel filling (#34) and the tunnel process (#35–#41) stay locked until U-04 / U-05 / U-06 are defined. Onboarding a running batch cannot move past those points either, because onboarding records history through the same gates (submit_activity from READY)

## 5 Engine changes
ID | Capability | Status | Why existing functionality cannot express it | Smallest change | Existing behaviour it could affect | How it will be tested
E-1 | Planning value unresolved, execution valid (G-3) | APPROVED — Option B (implement at migration) | publish_process_definition refuses when v_process_envelope.unplaced_activity_count > 0, and v_process_catalogue.is_selectable requires unplaced_activity_count = 0. Both read one expression in v_process_standard: count(*) FILTER (WHERE standard_start_hour IS NULL). Nothing can say 'no planned hour, on purpose'. create_master_batch only checks status = published; generate_activity_plan / repoint already leave planned_*_at NULL; validate_batch only WARNS (NO_BASELINE_HOUR). | process_activity.planning_unresolved boolean NOT NULL DEFAULT false; CHECK (NOT planning_unresolved OR standard_start_hour IS NULL); v_process_standard counts unplaced as standard_start_hour IS NULL AND NOT planning_unresolved, and adds unresolved_planning_count. Publish and is_selectable follow unchanged. | Only processes with flagged rows. Verified today: PROCESS-2026B 0 and 2026C 0 NULL-hour rows; ROUTE-2026A (archived) 17 NULL-hour rows, none flagged → all three unchanged. standard_hr / planned times read '—' for the new process. | Rolled back: (1) 2026B / 2026C / ROUTE-2026A unplaced counts and is_selectable identical before/after; (2) fixture draft with one unflagged NULL-hour row → publish refused naming 1; flag it → publishes; (3) batch → plan with NULL planned times → validate (warnings only) → activate → gate eligibility; (4) re-run 0081 task-manual (20) and 0080 lab/GM (20) suites.
E-2 | Passive hold timestamps (G-1) | APPROVED (implement at migration) | A hold opens READY; start_activity accepts it (a Supervisor 'start'); submit/complete_activity write actual_start = coalesce(actual_start, now()) = the confirmation time, made permanent by fn_actual_is_append_only. Nothing derives a hold's start from its predecessor. | (1) start_activity refuses is_hold rows. (2) submit_activity, is_hold rows only: actual_start = coalesce(actual_start, max(actual_end) of the codes in this activity's entry PREDECESSOR rule(s)); audit records start_source = 'predecessor_actual_end'; no predecessor end → actual_start stays NULL, never now(). Confirmation stays in submitted_at / submitted_by / actual_end. | Every is_hold activity in any process (2026C holds included; no batches exist). Hold duration/variance become predecessor-end → confirmation. Non-hold activities unchanged. | Rolled back: start_activity on a hold refused; confirm → actual_start = predecessor actual_end, submitted_by = confirmer, actual_end = server time; hold with no predecessor → actual_start NULL; non-hold submit unchanged; both suites re-run.
E-5 | Unresolved dependency keeps the activity blocked (NEW gap) | REQUIRED to represent U-03 / U-04 / U-05 / U-06 as blocked — for your decision | Every existing gate kind either OPENS when it has nothing to evaluate — PREDECESSOR naming no generated activity passes (total = 0); LAB_APPROVED with no binding and any unknown kind are 'unevaluable', which advance_batch does not treat as blocking; FIELD/SENSOR rules not dictated are 'skipped' — or means something else: GM_APPROVAL is a management decision (rejected for SOP ambiguity); ELAPSED_TIME with no hours and DAY0_DURATION with no duration fail forever but assert a missing TIME, and day0_duration_hr is frozen at activation. Leaving the dependency out opens the task early. | New gate kind 'UNRESOLVED_DEPENDENCY' in evaluate_gates: verdict always 'fail'; gate_rule.conflict_id required; blocked reason rendered from the template with the conflict_register question (e.g. 'Locked — the SOP does not yet define when this may start: <question> (U-03)'). No new table, no new RPC, no release path: the rule is resolved by defining it in process data (a new process version). | No existing rows use the kind → no current behaviour changes. Activities carrying it (and everything downstream) stay LOCKED — see U-19. Running batches that reach such a point wait for a defined rule; how a defined rule reaches an already-running batch is not designed yet. | Rolled back: activity with the gate stays LOCKED across advance_batch with the register question in blocked_reason; start/complete refused; downstream stays locked; all existing gate kinds unchanged; both suites re-run.
E-3 | Completed-only predecessor | DEFERRED — required only once U-04 is formally decided | gate_predecessor_status counts COMPLETED and SKIPPED as done; no way to require COMPLETED. | Optional config {"require":"COMPLETED"} on PREDECESSOR; gate_predecessor_status gains p_require text DEFAULT NULL (4-arg version replaced). | Only rules carrying the key (49 existing PREDECESSOR rules have none). | When implemented: skipped predecessor keeps the rule shut; completed opens it; rules without the key unchanged.
E-4 | 'Started' predecessor | DEFERRED — only relevant if U-12 lab timing is approved | PREDECESSOR opens only on COMPLETED/SKIPPED; no 'has started' condition. | Optional config {"when":"started"} (done = actual_start IS NOT NULL). | Only rules carrying the key. | When implemented: locked before the production task starts, open once started, never on a skip.
P-1 | GM_APPROVAL as containment | NOT APPLIED — temporary operational containment mechanism, pending factory decision | Existing: GM_APPROVAL gate {"checkpoint": N} passes only on a recorded GM decision (record_checkpoint_decision: GM only, reason mandatory, append-only, audited). | No change. Not placed on #14, #33 or #35: a GM approval does not define 0D, the tunnel-preparation start or the tunnel clock (U-18). | None. | —

## Confirmed
# | Confirmed
1 | Runtime baseline = new hardcoded version from the 31-08 Compost SOP, seeded as structured process data (no React conditionals; a future SOP replaces data, not code).
2 | Paddy (1C-A) and CM/mineral (1A) available from activation as parallel work.
3 | Holds/triggers confirmed manually by the Supervisor; hold start is process-derived (E-2, approved).
E-1 | Option B: planning_unresolved boolean (approved).
Unresolved rules | An unresolved factory rule stays unresolved and blocks execution at that point (E-5); it is never replaced by a GM approval, a fake predecessor or a missing predecessor.
Lab | Migrated lab behaviour = existing LAB-2026A behaviour. Timing proposals (U-12) are documentation only.
4 | TURNERPRCOESS governs explicit Turner / pile / bunker / tunnel values and sequence.
5 | Reload 2 optional — skip with reason (existing skip_activity + skip_policy, 0081).
6 | B1/B2/B3 open when the first pile of the pair (P1/P3/P5) completes T3.
7 | Supervisor records only readings the SOP task explicitly states.
8 | '+' → checklist only where it separates actions; full SOP wording kept as instruction.
Evidence | PERFORMED WORK / PHYSICAL / TURNER OPERATION → before + after photo (prompt.md §6–7). PASSIVE HOLD → none. TRIGGER CONFIRMATION → the trigger reading. Lab → existing checkpoint evidence.
Existing engine | Expressible today: per-pile/per-bunker chains (FIXED_LABEL + PREDECESSOR ALL), T1→T2 8 h minimum rest, convergence, bunker opening at first pile, serial tunnel filling, the 8 GM lab gates, optional Reload 2, photos after Start, readings, checklist items.
Modelling convention | One task per SOP line carrying hours is a TEMPORARY baseline convention. The data model already allows several activities to reference the same source line (source_ref is per activity; nothing enforces one-to-one).